## Sheet1
Week | Tasks | Description | Estimated Hours | Hours Used | Spare Hours | Reason For Spare hours | Overtime Hours | Reason For Overtime | Week Total
2 | Member User Stories | For the actions that each Member of the Game Café Expects to be able to take, as a member. | 2 | 0.905 | 1.095 | Task Time Overestimation | 0 | N/A | 4.41
| Staff User Stories | For the actions that each Staff Member at the Game Café Expects to be able to take, as a member of staff. | 2 | 1 | 1 | Task Time Overestimation | 0 | N/A
| Use Case Diagram | To show the actions that all Entities for the Game Café expect to be able to take. | 2 | 1.208 | 0.792 | Task Took Between 1 and 2 hours (suggested estimation values for the hours a task will take, are that of 1, 2, 4 and 8 (for hours)) | 0 | N/A
| Robustness Diagram | To describe the robustness of this system. | 2 | 1.297 | 0.703 | Task Took Between 1 and 2 hours (suggested estimation values for the hours a task will take, are that of 1, 2, 4 and 8 (for hours)) | 0 | N/A
3 | Decide on a Database Solution | To use with our C# Implementation | 2 | 1
| Conduct Research Into How to Link the Database with our C# Application | To be able to link the database with our C# Implementation | 2
| MVVM and/or MVC Research | For looking into the minimum requirement for the software pattern, we are to use in development | 2