## Sheet1
Phase | Week | Task | Description | Expected Hours (For the Whole Phase) | Expended Hours | Lost Hours (For the Whole Phase) | Reason For Lost Hours | Overtime Hours (For the Whole Phase) | Reason For Overtime | Week/Phase Sub-Total and Project Final Total
Prototype | 1 | GitHub Management | Handling conflicts and commitments to our team's GitHub Repository. | 3 | 0.75
|  | Health Power-Up | (Initial) Implementation of the Health Power-Up. The Player can collect this to restore their ship's health. | 1 | 0.5
|  | Attending Meetings | Meeting with other members of the team, to discuss what we intend to complete, for the current day/week. | 2 | 1 |  |  |  |  | 2.25
| 2 | Attending Meetings | Meeting with other members of the team, to discuss what we intend to complete, for the current day/week. | 2 | 0.3
|  | GitHub Management | Handling conflicts and commitments to our team's GitHub Repository. | 3 | 0.33
|  | Player UI Placeholder | For providing information to the Player (Ship's Health, Current Score, Active Weapon, Current Level etc.) | 2 | 0.75
|  | Level 0 Implementation | Basic implementation of the first level (splicing the sprite sheet, HUD display, basic Player logic etc.) | 1 | 1.25 | N/A | N/A | 0.25 | Issues in communication with merging our assets for the first level
|  | Resolving Scaling Issues | Assets in the Unity project were at a far greater scale then they should have, this was set back to 1/100th of the values in 1.0.5 for version 1.0.6 | 0.5 | 0.5 | N/A | N/A |  | N/A | 3.13
| 3 | Helping With Publisher Prototype | Helping Jack resolve issues with building the version of the project Prototype to show the publisher | 1 | 1 | N/A | N/A | N/A | N/A
|  | Attending Meetings | Meeting with other members of the team, to discuss what we intend to complete, for the current day/week. | 2 | 0.5 |  | Not meeting reguarly due to team-member absence | N/A | N/A | 1.5
PHASE SUB-TOTAL
6.88
Alpha | 4 | Github Management | Resolving issues with conflicts and commitments to our team's GitHub repository | 3 | 1.5 | 1.5 | Not devoting enough time for the task | N/A
|  | Implement a banner-ad | At the bottom of the screen, when the game is paused | 3 | 1.5 | 1.5 | Not devoting enough time for the task | N/A |  | 3
| 5 | AdMob Implementation Alteration | As per having to change the DeviceID for showing test adverts and altering the logic for when to show adverts | 3 | 0.5 | 2.5 | Not devoting enough time for the task | N/A | N/A | 0.5
PHASE SUB-TOTAL
3.5
Beta | 6 | Plus 50% health power-up |  | 2 | 0.33 | N/A | N/A
|  | Plus 100% health power-up |  | 2 | 1.1666 | N/A | N/A
|  | Double damage power-up |  | 2 | 0.2 | N/A | N/A
|  | Tempory inviciblity power-up |  | 2 | 0.2 | N/A | N/A
|  | Triple cash power-up |  | 2 | 0.2 | N/A | N/A
|  | 0.3x reload speed power-up |  | 2 | 0.41167 | N/A | N/A
|  | 2.5x speed power-up |  | 2 | 0.05 | N/A | N/A
|  | Nuke power-up (clear all enemies on screen) |  | 2 | 0.643 | N/A | N/A
|  | Freeze all enemies power-up |  | 2 | 0.31 | N/A | N/A
|  | Double points power-up |  | 2 | 0.2 | N/A | N/A
|  | Plus 5, 20 and 100 cash power-up |  | 2 | 0.5 | N/A | N/A | (FOR THE IMPLEMNTATION OF ALL POWER-UP ENTITIES) | (FOR THE IMPLEMNTATION OF ALL POWER-UP ENTITIES)
|  | Ship Upgrades System | For the Player to grant their ship greater health/speed, as well as for them to buy weapons (e.g. extra bullet, rocket) from | 2 | 0 | N/A | N/A | 2.2113 | Making sure that implementation is logical and consistant (for all types of power-up entities) | 4.2113
| 7 | Nuke power-up (clear all enemies on screen) |  |  | 0.333
|  | Ship Upgrades System | For the Player to grant their ship greater health/speed, as well as for them to buy weapons (e.g. extra bullet, rocket) from | 2 | 3 | N/A | N/A | 1 | The estimation for number of hours this task would take, would not match up to the number of hours it will actually take (not finished just yet)
|  | Group Meeting |  | 2 | 0.5 |  |  |  |  | 3.833
| 8 | Power-Up Manager | To spawn Power-Up Entities given certain settings | 3 | 0.8
0.8