## Sheet1
Week | Tasks | Description | Estimated Hours | Hours Used | Spare Hours | Reason For Spare hours | Overtime Hours | Reason For Overtime | Week Total
2 | Member User Stories | For the actions that each Member of the Game Café Expects to be able to take, as a member. | 2 | 0.905 | 1.095 | Task Time Overestimation | 0 | N/A | 4.41
| Staff User Stories | For the actions that each Staff Member at the Game Café Expects to be able to take, as a member of staff. | 2 | 1 | 1 | Task Time Overestimation | 0 | N/A
| Use Case Diagram | To show the actions that all Entities for the Game Café expect to be able to take. | 2 | 1.208 | 0.792 | Task Took Between 1 and 2 hours (suggested estimation values for the hours a task will take, are that of 1, 2, 4 and 8 (for hours)) | 0 | N/A
| Robustness Diagram | To describe the robustness of this system. | 2 | 1.297 | 0.703 | Task Took Between 1 and 2 hours (suggested estimation values for the hours a task will take, are that of 1, 2, 4 and 8 (for hours)) | 0 | N/A
3 | Decide on a Database Solution | To use with our C# Implementation | 2 | 2 | 0 | N/A | 0 | N/A | 9
| Conduct Research Into How to Link the Database with our C# Application | To be able to link the database with our C# Implementation | 2 | 2 | 0 | N/A | 0 | N/A
| MVVM and/or MVC Research | For looking into the minimum requirement for the software pattern, we are to use in development | 2 | 2 | 0 | N/A | 0 | N/A
| Create Member and Booking Model Classes and the basic system Forms | Assemble the first Prototype of the software project | 3 | 3 | 0 | N/A | 0 | N/A
4 | Assemble Prototype for Database Solution implementation | Put together the first prototype, that uses the database solution that has been decided upon by the team. | 3 | 3 | 0 | N/A | 0 | N/A | 3
5 | Implement Exit Program Confirmation | So if the User attempts to close a form, the program will ask them to confirm as to whether they would want to terminate the whole application or not. | 3 | 4 | 0 | N/A | 1 | Underestimating the time it would take to implement this feature, given the nuances that were not considered before going about this implementation. | 4
6 | Create a Software Class | Create a Software Class, for Visual Studio to use as a model for the Software Database Table. | 1 | 1 | 0 | N/A | 0 | N/A | 1
| Create a Hardware Class | Create a Hardware Class, for Visual Studio to use as a model for the Hardware Database Table. | 1 | 1 | 0 | N/A | 0 | N/A | 1
9 | Create a custom Form to use as a Confirmation Dialog | Create a custom form that can be used modally, instead of the default dialog window. | 4 | 6 | 0 | N/A | 2 | Not considering the aspects of a Form that would have to be considered, for a custom Modal Dialog window. | 6
10 | Finalise Management System Logic | Add in the remaining logic for the management system (allowing Users to add information to the database and manipulate it as required, as well as maintaining the correct Form traversal. | 3 | 3 | 0 | N/A | 0 | N/A | 3
11 | Finalise Management System Logic | Add in the remaining logic for the management system (allowing Users to add information to the database and manipulate it as required, as well as maintaining the correct Form traversal. | 3 | 3 | 0 | N/A | 0 | N/A | 3